## Case background and team
Take home workplanning activity for L.E.K. Consulting 2nd round interviews
CASE BACKGROUND:
• Our client, FruityFruits, is a national producer of fruit products. Their products include freeze dried fruit snacks (strawberries and mangoes) and fresh cut fruit (strawberries, mangoes, and pineapples). These are the only products that they currently produce. • FruityFruits currently sells via select grocery store chains (Albertsons and Publix) and they also sell DTC via their own website (not Amazon). • FruityFruits would like L.E.K. to size FruityFruits's current market (fresh cut and freeze dried fruits), identify key purchasing criteria (KPCs) for fruit products, assess their performance on those KPCs relative to competitors, identify a new product for FruityFruits to expand into (e.g., gummy fruit snacks) and align with FruityFruits on this growth opportunity, and size FruityFruits's expansion opportunity.
CASE LOGISTICS:
• FruityFruits hired L.E.K. for a 6 week long engagement. L.E.K. team assigned to the case consists of 3 associates of various seniority, 1 consultant, 1 engagement manager, and 1 managing director
| TEAM MEMBERS: | LEVEL: | CASE ALLOCATION: | TEAM MEMBER BACKGROUND:
| Jane Jones | First year associate | 6 weeks | Jane joined L.E.K. two months ago out of undergrad and this is her second case. She is eager, though fairly inexperienced and cannot yet manage significant quantitative tasks without a lot of oversight
| Matt Miller | Second year associate | 6 weeks | Matt has been at L.E.K. for just over a year. He has been feeling burnt out and also somewhat let down. He was looking forward to getting quantitative modeling experience, but when he got the opportunity he made a few significant mistakes, and so on subsequent cases he was not trusted with analytical work.
| Wilma Williams | Fourth year associate | 3 weeks (first) | Wilma has been at L.E.K. for over three years and is an established high performer and is looking to be promoted to Consultant level in 3-6 months. She is very experienced in quantitative modeling, has done it numerous times, and is looking to improve other skills (such as crafting a story with slides, overseeing more junior associates, or presenting to clients).
| You | Consultant | 6 weeks | You are the consultant on the FruityFruits case, tasked with running the day to day activities and ensuring associates complete their assigned tasks timely and error-free | \
| Dave Duncan | Engagement manager | 6 weeks | Dave has been at L.E.K. for 2 years and was recently promoted to his current position. While he has worked on other consumer products, he has limited experience in food and beverage and will be relying on research conducted by the team to get into the intricacies of the industry
| Laura Lawrence | Managing director | 6 weeks | Laura is L.E.K.'s leading food and beverage expert. She advises all of L.E.K.'s top food and beverage clients and has authored several thought leading articles on the future of food and beverage industry. She will primarily focus on ensuring that interim and final readouts for FruityFruits go smoothly

## BLANK issue map & workplan
Take home workplanning activity for L.E.K. Consulting 2nd round interviews
TASK #1:
There are four key questions that must be answered as part of the FruityFruits engagement. Two of them are already filled in below (#1 and #2). TASK: Your task is to 1) fill in remaining two key questions (numbered #3 and #4), and 2) for all four key questions, please type sub-questions that you would need to answer to get to the answer for each bolded element
1. What Key Purchasing Criteria (KPCs) are most improtant for fruit products?
►[Type question]
►[Type question]
►[Type question]
2. What is FruityFruits's performance relative to competitors?
►[Type question]
►[Type question]
►[Type question]
3. [Type key question]
►[Type question]
►[Type question]
►[Type question]
4. [Type key question]
►[Type question]
►[Type question]
►[Type question]
TASK #2:
| Different types of research and analysis that L.E.K. typically conducts for a case are shown below. Please read them and their descriptions carefully. To the right of research / analysis you will find a list of potential activities that may be relevant to this case (team management and content generation may not necessarily be captured in the list). |  |  | TASK: In the blank workplan table, please highlight activities from the list on the left and proposed Associate owners for those activities. NOTE that not all activities listed on the left are relevant to this case, and your task is to 1) identify which activities are relevant to this case, 2) propose for how long each activity should be conducted, and 3) propose an Associate to own the activity. Please also fill in proposed content for the interim and final client presentations at the bottom of the workplan table
| Research and analysis types and descriptions: | Activity # | Activity list:
| Interviews: |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Notes: | Directions to fill out the blank workplan:
| Phone interviews conducted with various stakeholders to gather qualitative insights. • Typically take 2-5 weeks to complete • Typically conducted by 1st or 2nd year Associates • Take up ~50% of Associate's time (multiple types of interviews can be done concurrently) | 1 | Interviews with FruityFruits customers | [7 empty] | Week 1 | Week 2 | Week 3
|  | 2 | Interviews with FruityFruits competitors | [7 empty] | Yes Owner(s): X | Yes Owner(s): X
|  | 3 | Interviews with distributors of FruityFruits products | [7 empty] | Enter "Yes" if activity is in progress during a specific week. Enter the team member(s) owning the activity underneath. |  | If activity is not to be performed during a specific week, leave the cell blank.
|  | 4 | Interviews with internal L.E.K. experts
|  | 5 | Interviews with FruityFruits internal manufacturing team to identify cost reductions
Survey:
| Online survey sent to various stakeholders to fill out; results are analyzed by L.E.K. team • Typically take 3 weeks to complete • Typically conducted by 2nd, 3rd, or 4th year Associates • Take up ~75% of Associate's time (but multiple surveys can be run concurrently) | 6 | Survey to assess customer price sensitivity
|  | 7 | Survey to identify inefficiencies in FruityFruits distribution process
|  | 8 | Survey to assess geographic distribution of different types of fruit products
|  | 9 | Survey to asses customer perception of loyalty programs for fruit products
Model:
| Quantitative excel model built by L.E.K. team to create a forecast or size a market • Typically take 3 weeks to complete • Typically conducted by 2nd, 3rd, or 4th year Associates • Takes up ~75% of Associate's time, but can can be done concurently with secondary reseach or second model (if not overly complex) | 10 | Model building to size freeze dried fruit market
|  | 11 | Model building to size gummy fruit snacks market
|  | 12 | Model building to size fresh fruit market
|  | 13 | Model building to size FruityFruits's expansion opportunity
Secondary research
| Secondary research to aggregate information or gather inputs for surveys / models. • Typically take 1-3 weeks to complete • Conducted by all Associate levels • Take up <20% of Associate's time, so can be done concurrently with most other activities | 14 | Secondary research to identify fruit products KPCs
|  | 15 | Secondary research to identify geographic spread of FruityFruits competitors
|  | 16 | Secondary research to identify potential expansion opportunities
|  | 17 | Secondary research for model inputs
Geographic analysis
| Geographic analysis conducted in Tableau (data visualization software). • Typically takes 1 week to complete and ~75% of Associate's time • Conducted by 2nd, 3rd, or 4th year Associates | 18 | Geographic analysis to identify new geographic expansion areas for FruityFruits
Pricing analysis
| Quantitative price sensitivity analysis done in Excel. • Typically takes 2 weeks to complete and ~75% of Associate's time • Conducted by 2nd, 3rd, or 4th year Associates | 19 | Consumer price sensitivity analysis
Client alignment
| Client alignment on key case issues (typically done during client readouts) • Typically done by 4th year Associates or Consultants / Managers | 20 | Client meeting to align on an expansion opportunity for FruityFruits
[6 empty] | ▲ |  |  | ▲
[6 empty] | Interim client readout |  |  | Final client readout
[6 empty] | Readout content: • [Fill in] • [Fill in] • [Fill in] |  |  | Readout content: • [Fill in] • [Fill in] • [Fill in]